# Complete Work Management SaaS

Phase-by-Phase Build Roadmap | Step-by-Step Execution Guide

Version 1.0  •  26 October 2026  •  Source: Work Management Platform — Complete Development Blueprint

উদ্দেশ্য: প্রতিটি phase-এর কাজ, deliverables, testing এবং approval gate সম্পন্ন করে একটি production-ready multi-tenant SaaS তৈরি করা। এই ডকুমেন্ট development execution plan; সফটওয়্যার তৈরি হয়ে গেছে এমন দাবি নয়।

# Roadmap at a glance

Phase 0: Requirements, UX & planning  |  1–2 weeks

Phase 1: Engineering foundation & UI shell  |  1–2 weeks

Phase 2: Database, authentication & security  |  2–3 weeks

Phase 3: Profiles, workspaces & invitations  |  1–2 weeks

Phase 4: Projects, custom sections & tasks  |  3–5 weeks

Phase 5: SEO, keyword research & topical maps  |  3–4 weeks

Phase 6: Social, calendar, accounts & files  |  2–3 weeks

Phase 7: Notifications, search & dashboards  |  2–3 weeks

Phase 8: PDF reports & exports  |  1–2 weeks

Phase 9: QA, hardening & production launch  |  2–4 weeks

Estimated overall planning range: 18–28+ weeks for a small experienced team. Individual phase estimates may overlap; this is not a delivery guarantee.

# How to execute every phase

1. Phase backlog-এর প্রতিটি item একজন owner-কে assign করুন।

2. Frontend + backend + schema + validation + authorization + tests একসঙ্গে implement করুন।

3. Pull request review, staging deployment এবং acceptance test চালান।

4. Gate pass না হলে পরের dependent phase-কে complete বলবেন না।

5. Deliverables, test evidence, unresolved issues ও approval date record করুন।

# Phase 0 — Requirements, UX & planning

Estimated duration: 1–2 weeks

## Step-by-step implementation checklist

☐ Step 1. পুরো scope থেকে epics, user stories এবং acceptance criteria তৈরি করুন।

☐ Step 2. Owner/Admin/Manager/Member-এর permission matrix ও task review lifecycle final করুন।

☐ Step 3. Sitemap, user journey, wireframes, ERD এবং prioritized backlog তৈরি করুন।

☐ Step 4. UI branding, design tokens ও sample monthly report layout approve করুন.

## Required deliverables

PRD • UX wireframes • ERD • Permission matrix • Prioritized backlog

## Acceptance gate / Done criteria

PRD, UX map, ERD এবং roles অনুমোদিত।

Status: ☐ Not started   ☐ In progress   ☐ Testing   ☐ Approved     Owner: __________   Date: __________

# Phase 1 — Engineering foundation & UI shell

Estimated duration: 1–2 weeks

## Step-by-step implementation checklist

☐ Step 1. GitHub repository, Next.js App Router, React, strict TypeScript initialize করুন।

☐ Step 2. Tailwind CSS, shadcn/ui/Radix, typography, light/dark theme setup করুন।

☐ Step 3. Responsive sidebar, navigation, reusable form/table/card/dialog, loading/error/empty states তৈরি করুন।

☐ Step 4. Lint, typecheck, test, build scripts এবং preview CI চালু করুন।

## Required deliverables

Working app shell • Reusable UI library • GitHub repository • CI checks

## Acceptance gate / Done criteria

Desktop/mobile shell কাজ করে; lint, typecheck, tests ও build pass।

Status: ☐ Not started   ☐ In progress   ☐ Testing   ☐ Approved     Owner: __________   Date: __________

# Phase 2 — Database, authentication & security

Estimated duration: 2–3 weeks

## Step-by-step implementation checklist

☐ Step 1. Supabase project, PostgreSQL migrations, keys/constraints/indexes তৈরি করুন।

☐ Step 2. Email signup, verification, login/logout, password recovery, Google OAuth ও MFA configure করুন।

☐ Step 3. SSR cookie sessions, auth callbacks, server-side validation এবং authorization helpers লিখুন।

☐ Step 4. Workspace-level RLS, Storage policies, SQL cross-tenant denial tests implement করুন।

☐ Step 5. Service credentials server-only রাখুন; secrets Git বা browser-এ পাঠাবেন না।

## Required deliverables

Initial SQL migrations • Working auth flows • RLS policies • Security tests

## Acceptance gate / Done criteria

Unauthorized access বন্ধ; দুই workspace-এর data isolation app ও SQL test-এ pass।

Status: ☐ Not started   ☐ In progress   ☐ Testing   ☐ Approved     Owner: __________   Date: __________

# Phase 3 — Profiles, workspaces & invitations

Estimated duration: 1–2 weeks

## Step-by-step implementation checklist

☐ Step 1. Profile edit, avatar/cover, bio, skills, links, theme, timezone ও privacy settings তৈরি করুন।

☐ Step 2. Personal/company workspace create, edit, switch ও settings implement করুন।

☐ Step 3. Invite, accept, revoke, remove, role change ও ownership transfer flow তৈরি করুন।

☐ Step 4. Invite expiry, single-use token, email match এবং last-owner rule test করুন।

## Required deliverables

Profile screens • Workspace screens • Invitation workflow • Role tests

## Acceptance gate / Done criteria

তিনজন test user invitation দিয়ে join করে কেবল permitted data দেখতে পারে।

Status: ☐ Not started   ☐ In progress   ☐ Testing   ☐ Approved     Owner: __________   Date: __________

# Phase 4 — Projects, custom sections & tasks

Estimated duration: 3–5 weeks

## Step-by-step implementation checklist

☐ Step 1. Project CRUD, project members, nested sections, reorder ও permissions তৈরি করুন।

☐ Step 2. No-code field types, records, relationships, saved views, table/kanban/calendar/gallery implement করুন।

☐ Step 3. CSV/XLSX import-export, filtering, sorting, archive এবং validation যোগ করুন।

☐ Step 4. Task assignment, checklist, comments, time tracking, attachments, evidence ও submission implement করুন।

☐ Step 5. Approve/request-changes review queue, status history ও audit event যোগ করুন।

## Required deliverables

Projects module • Dynamic section builder • Task workflow • Approval queue

## Acceptance gate / Done criteria

Member task submit করতে পারে; authorized reviewer approve করে; unauthorized reviewer পারে না।

Status: ☐ Not started   ☐ In progress   ☐ Testing   ☐ Approved     Owner: __________   Date: __________

# Phase 5 — SEO, keyword research & topical maps

Estimated duration: 3–4 weeks

## Step-by-step implementation checklist

☐ Step 1. Website metadata, SEO activity records, work URL, reusable checklists তৈরি করুন।

☐ Step 2. Keyword manual entry, CSV/XLSX import preview, mapping, deduplication, filters, exports implement করুন।

☐ Step 3. Keyword clusters, source-attributed metrics ও topic relationships তৈরি করুন।

☐ Step 4. React Flow-তে pillar/subtopic nodes, edges, zoom, autosave, keyword links ও table view তৈরি করুন।

## Required deliverables

SEO tracker • Keyword manager • Topical map editor • Import tests

## Acceptance gate / Done criteria

Imported data অপরিবর্তিত থাকে; map nodes/links logout-login পরেও থাকে।

Status: ☐ Not started   ☐ In progress   ☐ Testing   ☐ Approved     Owner: __________   Date: __________

# Phase 6 — Social, calendar, accounts & files

Estimated duration: 2–3 weeks

## Step-by-step implementation checklist

☐ Step 1. Social account registry, draft/scheduled/published content, URLs ও thumbnails তৈরি করুন।

☐ Step 2. Task/social record-এর সঙ্গে linked month/week/list calendar implement করুন।

☐ Step 3. Secure account directory-তে কেবল vault reference রাখুন, password নয়।

☐ Step 4. Private uploads, signed downloads, access audits ও file deletion flow implement করুন।

## Required deliverables

Social tracker • Calendar • Account directory • Private file storage

## Acceptance gate / Done criteria

Calendar sync, published URL recording এবং cross-workspace private file denial pass।

Status: ☐ Not started   ☐ In progress   ☐ Testing   ☐ Approved     Owner: __________   Date: __________

# Phase 7 — Notifications, search & dashboards

Estimated duration: 2–3 weeks

## Step-by-step implementation checklist

☐ Step 1. Assignment, comments, due dates, reviews ও invites-এর in-app notifications তৈরি করুন।

☐ Step 2. Permission-filtered global search, activity log, audit events ও command menu তৈরি করুন।

☐ Step 3. Personal ও owner dashboards-এ genuine KPI queries, filters, charts ও widgets যোগ করুন।

☐ Step 4. No data হলে honest empty state দেখান; fake analytics নয়।

## Required deliverables

Notification center • Activity history • Search • Role-aware dashboards

## Acceptance gate / Done criteria

Task update করলে correct KPI/notification update হয়; unauthorized search leakage নেই।

Status: ☐ Not started   ☐ In progress   ☐ Testing   ☐ Approved     Owner: __________   Date: __________

# Phase 8 — PDF reports & exports

Estimated duration: 1–2 weeks

## Step-by-step implementation checklist

☐ Step 1. Month/employee/project/type filter সহ report configuration তৈরি করুন।

☐ Step 2. SEO, social, employee, project ও combined report templates implement করুন।

☐ Step 3. Branded multi-page PDF, tables, hyperlinks, page numbers, date ও accurate totals যোগ করুন।

☐ Step 4. Private preview/download, report metadata এবং Vercel runtime compatibility test করুন।

## Required deliverables

PDF templates • Report generator • Secure downloads

## Acceptance gate / Done criteria

PDF-এর সংখ্যা source data-এর সঙ্গে মেলে; unauthorized download blocked।

Status: ☐ Not started   ☐ In progress   ☐ Testing   ☐ Approved     Owner: __________   Date: __________

# Phase 9 — QA, hardening & production launch

Estimated duration: 2–4 weeks

## Step-by-step implementation checklist

☐ Step 1. Unit, integration, Playwright E2E এবং SQL/RLS test suite চালান।

☐ Step 2. Auth, CSRF, SSRF, rate limiting, permissions, file access, audit ও secrets review করুন।

☐ Step 3. Large data, pagination, import, report, accessibility ও mobile responsiveness test করুন।

☐ Step 4. Backup/restore, migration rollback, monitoring এবং incident runbook প্রস্তুত করুন।

☐ Step 5. GitHub → Vercel deployment, DNS/HTTPS, callbacks ও production smoke tests করুন।

## Required deliverables

QA report • Deployment guide • Rollback runbook • Production release

## Acceptance gate / Done criteria

Critical issue zero; real production auth, invite, upload, isolation ও PDF smoke tests pass।

Status: ☐ Not started   ☐ In progress   ☐ Testing   ☐ Approved     Owner: __________   Date: __________

# Core technical architecture

Frontend: Next.js App Router, React, strict TypeScript, Tailwind CSS, shadcn/ui, Radix.

Backend/data: Next.js server handlers/actions, Supabase PostgreSQL, Supabase Auth, RLS, private Storage.

Data/UI: React Hook Form + Zod, TanStack Table, Recharts, React Flow, CSV/XLSX libraries.

Quality/deployment: Vitest, Testing Library, Playwright, SQL/RLS tests, GitHub CI, Vercel.

# Release-wide non-negotiable checklist

☐ All required modules work with real data, not mocked-only screens.

☐ Owner/Admin/Manager/Member permissions enforced server-side.

☐ Every workspace-owned table and private file enforces tenant isolation.

☐ Auth, invitations, task approvals, imports, search and PDF access tested end-to-end.

☐ No plaintext passwords/recovery codes in database, logs or exports.

☐ Responsive desktop/tablet/mobile and accessible keyboard flows verified.

☐ typecheck, lint, tests, production build, migrations and smoke tests pass.

☐ README, .env.example, source, deployment/rollback instructions delivered.

# Scope boundary

Source blueprint অনুযায়ী subscription billing, automatic SEO data collection, automatic social API posting, full password manager এবং automated Google ranking tracking এই release-এর বাইরে। এগুলোকে আলাদা future roadmap-এ plan করতে হবে।

# First sprint — immediate action list

☐ Set up version-pinned Next.js repository and CI.

☐ Create public auth screens and real Supabase SSR authentication.

☐ Migrate profiles, preferences, workspaces, members, invitations and RLS.

☐ Implement requireUser, requireWorkspaceMember and permission service.

☐ Create responsive workspace shell and onboarding.

☐ Test three users, invitations and cross-workspace access denial.

☐ Deliver README, .env.example and local setup guide.

Sprint exit: Signup → email verification → profile edit → workspace create → invitation → login → cross-workspace denial works with real Supabase.